## Sheet1
Request_id | Department | Source_system | Location | Section_id | Asset_id | Asset_type | Work_description | Maintenance_category | Defect_id | Defect_severity | Failure_risk | Safety_related | Asset_operational_status | Affected_asset_quantity | Last_maintenance_date | Due_date | Overdue | Estimated_duration_minutes | Required_resources | Requires_block | Block_type_required | Preferred_date | Preferred_start_time | Preferred_end_time | Request_status
SMMS-001 | SIGNAL & TELECOM | SMMS | STN12 | SEC03 | SIG-135 | SIGNAL | Repair point machine malfunction near 181.2 | Corrective | DEF-4113 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-02-24 | 2026-09-14 | FALSE | 150 | 2 technicians, relay test set | TRUE | PARTIAL | 2026-09-14 | 20:00 | 23:00 | COMPLETED
SMMS-002 | SIGNAL & TELECOM | SMMS | STN14 | SEC04 | SIG-103 | SIGNAL | Replace faulty signal relay near 167.6 | Preventive | DEF-2678 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2025-08-09 | 2026-08-18 | TRUE | 240 | 4 technicians, cable jointing kit | TRUE | PARTIAL | 2026-08-25 | 02:00 | 05:00 | PENDING
SMMS-003 | SIGNAL & TELECOM | SMMS | STN11 | SEC03 | SIG-163 | SIGNAL | Replace degraded signal cable insulation near 106.9 | Preventive | DEF-2218 | CRITICAL | HIGH | FALSE | OUT_OF_SERVICE | 2 | 2025-10-22 | 2026-09-14 | FALSE | 150 | 2 technicians, relay test set | TRUE | FULL | 2026-09-16 | 01:00 | 04:00 | PENDING
SMMS-004 | SIGNAL & TELECOM | SMMS | STN06 | SEC07 | SIG-154 | SIGNAL | Replace degraded signal cable insulation near 154.8 | Preventive | DEF-2589 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2026-04-09 | 2026-09-04 | FALSE | 180 | 3 signal technicians, testing kit | TRUE | PARTIAL | 2026-09-06 | 20:00 | 00:00 | APPROVED
SMMS-005 | SIGNAL & TELECOM | SMMS | STN03 | SEC08 | SIG-188 | SIGNAL | Update interlocking software at 155.8 | Corrective | DEF-6373 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-01-24 | 2026-08-15 | TRUE | 150 | 2 technicians, relay test set | TRUE | PARTIAL | 2026-08-25 | 02:00 | 04:00 | PENDING
SMMS-006 | SIGNAL & TELECOM | SMMS | STN15 | SEC06 | SIG-140 | SIGNAL | Replace degraded signal cable insulation near 172.7 | Corrective | DEF-9456 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2025-11-13 | 2026-09-01 | FALSE | 150 | 4 technicians, cable jointing kit | TRUE | PARTIAL | 2026-09-04 | 20:00 | 23:00 | COMPLETED
SMMS-007 | SIGNAL & TELECOM | SMMS | STN06 | SEC07 | SIG-122 | SIGNAL | Repair point machine malfunction near 113.2 | Corrective | DEF-8444 | CRITICAL | HIGH | FALSE | OUT_OF_SERVICE | 1 | 2025-09-11 | 2026-09-07 | FALSE | 90 | 2 technicians, relay test set | TRUE | FULL | 2026-09-10 | 20:00 | 22:00 | APPROVED
SMMS-008 | SIGNAL & TELECOM | SMMS | STN11 | SEC05 | SIG-110 | SIGNAL | Update interlocking software at 183.8 | Corrective | DEF-2726 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-05-25 | 2026-09-18 | FALSE | 150 | 3 signal technicians, testing kit | TRUE | PARTIAL | 2026-09-20 | 20:00 | 22:00 | APPROVED
SMMS-009 | SIGNAL & TELECOM | SMMS | STN12 | SEC07 | SIG-143 | SIGNAL | Repair point machine malfunction near 50.4 | Preventive | DEF-6455 | HIGH | HIGH | TRUE | RESTRICTED | 2 | 2025-10-19 | 2026-09-17 | FALSE | 150 | 3 signal technicians, testing kit | TRUE | FULL | 2026-09-19 | 04:00 | 07:00 | APPROVED
SMMS-010 | SIGNAL & TELECOM | SMMS | STN01 | SEC07 | SIG-167 | SIGNAL | Replace degraded signal cable insulation near 145.1 | Corrective | DEF-1166 | LOW | LOW | FALSE | NORMAL | 1 | 2026-06-25 | 2026-09-08 | FALSE | 240 | 2 signal engineers, laptop with S&T software | TRUE | PARTIAL | 2026-09-08 | 04:00 | 08:00 | COMPLETED
SMMS-011 | SIGNAL & TELECOM | SMMS | STN10 | SEC03 | SIG-135 | SIGNAL | Update interlocking software at 188.3 | Predictive | DEF-1970 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-04-02 | 2026-09-04 | FALSE | 150 | 2 technicians, relay test set | TRUE | FULL | 2026-09-05 | 04:00 | 07:00 | APPROVED
SMMS-012 | SIGNAL & TELECOM | SMMS | STN07 | SEC01 | SIG-123 | SIGNAL | Replace faulty signal relay near 144.3 | Corrective | DEF-4856 | HIGH | HIGH | TRUE | RESTRICTED | 2 | 2025-08-31 | 2026-09-14 | FALSE | 180 | 2 technicians, relay test set | TRUE | FULL | 2026-09-14 | 02:00 | 04:00 | PENDING
SMMS-013 | SIGNAL & TELECOM | SMMS | STN16 | SEC07 | SIG-151 | SIGNAL | Replace degraded signal cable insulation near 36.9 | Predictive | DEF-6604 | LOW | LOW | FALSE | NORMAL | 1 | 2025-08-10 | 2026-09-19 | FALSE | 240 | 2 technicians, relay test set | TRUE | PARTIAL | 2026-09-23 | 04:00 | 07:00 | PENDING
SMMS-014 | SIGNAL & TELECOM | SMMS | STN08 | SEC03 | SIG-101 | SIGNAL | Update interlocking software at 153.3 | Predictive | DEF-7087 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2025-09-29 | 2026-09-17 | FALSE | 180 | 2 signal engineers, laptop with S&T software | TRUE | FULL | 2026-09-19 | 00:00 | 04:00 | APPROVED
SMMS-015 | SIGNAL & TELECOM | SMMS | STN09 | SEC03 | SIG-166 | SIGNAL | Repair point machine malfunction near 147.8 | Corrective | DEF-3468 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-02-14 | 2026-09-17 | FALSE | 120 | 2 technicians, relay test set | TRUE | FULL | 2026-09-18 | 22:00 | 02:00 | COMPLETED
SMMS-016 | SIGNAL & TELECOM | SMMS | STN15 | SEC03 | SIG-110 | SIGNAL | Replace degraded signal cable insulation near 20.2 | Predictive | DEF-9903 | LOW | LOW | FALSE | NORMAL | 1 | 2025-08-16 | 2026-09-17 | FALSE | 180 | 2 technicians, relay test set | TRUE | PARTIAL | 2026-09-17 | 04:00 | 08:00 | PENDING
SMMS-017 | SIGNAL & TELECOM | SMMS | STN16 | SEC02 | SIG-120 | SIGNAL | Update interlocking software at 149.6 | Predictive | DEF-6102 | LOW | LOW | FALSE | NORMAL | 1 | 2026-03-12 | 2026-08-17 | TRUE | 240 | 2 signal engineers, laptop with S&T software | TRUE | PARTIAL | 2026-08-29 | 04:00 | 08:00 | PENDING
SMMS-018 | SIGNAL & TELECOM | SMMS | STN13 | SEC08 | SIG-186 | SIGNAL | Replace faulty signal relay near 128.4 | Corrective | DEF-2997 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2025-12-24 | 2026-08-19 | TRUE | 150 | 2 signal engineers, laptop with S&T software | TRUE | FULL | 2026-08-30 | 01:00 | 03:00 | PENDING
SMMS-019 | SIGNAL & TELECOM | SMMS | STN10 | SEC08 | SIG-143 | SIGNAL | Repair point machine malfunction near 147.8 | Preventive | DEF-2424 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2025-08-15 | 2026-08-24 | TRUE | 150 | 2 technicians, relay test set | TRUE | PARTIAL | 2026-08-27 | 22:00 | 01:00 | PENDING
SMMS-020 | SIGNAL & TELECOM | SMMS | STN04 | SEC05 | SIG-118 | SIGNAL | Repair axle counter fault near 179.8 | Preventive | DEF-3153 | CRITICAL | HIGH | TRUE | OUT_OF_SERVICE | 1 | 2025-10-29 | 2026-09-05 | FALSE | 90 | 2 technicians, relay test set | TRUE | FULL | 2026-09-08 | 04:00 | 06:00 | PENDING
SMMS-021 | SIGNAL & TELECOM | SMMS | STN11 | SEC02 | SIG-154 | SIGNAL | Replace faulty signal relay near 23.6 | Predictive | DEF-3278 | LOW | LOW | FALSE | NORMAL | 1 | 2026-04-07 | 2026-08-22 | TRUE | 180 | 2 signal engineers, laptop with S&T software | TRUE | PARTIAL | 2026-08-28 | 04:00 | 06:00 | PENDING
SMMS-022 | SIGNAL & TELECOM | SMMS | STN01 | SEC01 | SIG-133 | SIGNAL | Repair axle counter fault near 139.5 | Corrective | DEF-6607 | LOW | LOW | FALSE | NORMAL | 1 | 2026-01-15 | 2026-08-30 | FALSE | 300 | 2 signal engineers, laptop with S&T software | TRUE | PARTIAL | 2026-09-04 | 20:00 | 00:00 | PENDING
SMMS-023 | SIGNAL & TELECOM | SMMS | STN08 | SEC06 | SIG-145 | SIGNAL | Replace faulty signal relay near 150.9 | Preventive | DEF-9412 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2025-08-17 | 2026-08-25 | FALSE | 180 | 2 technicians, relay test set | TRUE | FULL | 2026-08-27 | 20:00 | 23:00 | APPROVED
SMMS-024 | SIGNAL & TELECOM | SMMS | STN11 | SEC04 | SIG-142 | SIGNAL | Repair point machine malfunction near 148.7 | Corrective | DEF-6917 | CRITICAL | HIGH | TRUE | OUT_OF_SERVICE | 1 | 2026-02-21 | 2026-09-14 | FALSE | 120 | 2 technicians, relay test set | TRUE | FULL | 2026-09-18 | 04:00 | 08:00 | PENDING
SMMS-025 | SIGNAL & TELECOM | SMMS | STN01 | SEC02 | SIG-136 | SIGNAL | Replace degraded signal cable insulation near 108.7 | Preventive | DEF-6957 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-04-01 | 2026-09-05 | FALSE | 240 | 4 technicians, cable jointing kit | TRUE | PARTIAL | 2026-09-09 | 01:00 | 03:00 | COMPLETED
SMMS-026 | SIGNAL & TELECOM | SMMS | STN13 | SEC02 | SIG-178 | SIGNAL | Update interlocking software at 89.1 | Preventive | DEF-1267 | HIGH | HIGH | TRUE | RESTRICTED | 2 | 2026-03-26 | 2026-08-23 | TRUE | 150 | 3 signal technicians, testing kit | TRUE | FULL | 2026-08-27 | 22:00 | 02:00 | PENDING
SMMS-027 | SIGNAL & TELECOM | SMMS | STN02 | SEC07 | SIG-182 | SIGNAL | Repair axle counter fault near 37.1 | Preventive | DEF-3371 | HIGH | HIGH | TRUE | RESTRICTED | 2 | 2026-04-20 | 2026-08-31 | FALSE | 180 | 3 signal technicians, testing kit | TRUE | FULL | 2026-09-01 | 20:00 | 23:00 | PENDING
SMMS-028 | SIGNAL & TELECOM | SMMS | STN04 | SEC07 | SIG-167 | SIGNAL | Update interlocking software at 144.1 | Corrective | DEF-9530 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2025-11-01 | 2026-09-10 | FALSE | 180 | 3 signal technicians, testing kit | TRUE | PARTIAL | 2026-09-13 | 00:00 | 04:00 | PENDING
SMMS-029 | SIGNAL & TELECOM | SMMS | STN04 | SEC07 | SIG-157 | SIGNAL | Repair axle counter fault near 140.4 | Corrective | DEF-7499 | CRITICAL | HIGH | FALSE | OUT_OF_SERVICE | 2 | 2026-01-13 | 2026-09-03 | FALSE | 150 | 3 signal technicians, testing kit | TRUE | FULL | 2026-09-07 | 00:00 | 02:00 | APPROVED
SMMS-030 | SIGNAL & TELECOM | SMMS | STN06 | SEC05 | SIG-128 | SIGNAL | Repair point machine malfunction near 126.5 | Preventive | DEF-7907 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-05-22 | 2026-09-07 | FALSE | 120 | 2 technicians, relay test set | TRUE | FULL | 2026-09-11 | 04:00 | 08:00 | PENDING
SMMS-031 | SIGNAL & TELECOM | SMMS | STN15 | SEC08 | SIG-157 | SIGNAL | Repair point machine malfunction near 5.1 | Preventive | DEF-7508 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-01-24 | 2026-08-16 | TRUE | 180 | 2 technicians, relay test set | TRUE | PARTIAL | 2026-08-27 | 01:00 | 03:00 | PENDING
SMMS-032 | SIGNAL & TELECOM | SMMS | STN02 | SEC06 | SIG-125 | SIGNAL | Update interlocking software at 62.0 | Corrective | DEF-6802 | CRITICAL | HIGH | FALSE | OUT_OF_SERVICE | 1 | 2026-04-14 | 2026-09-14 | FALSE | 90 | 2 technicians, relay test set | TRUE | FULL | 2026-09-15 | 01:00 | 04:00 | APPROVED
SMMS-033 | SIGNAL & TELECOM | SMMS | STN11 | SEC01 | SIG-189 | SIGNAL | Replace degraded signal cable insulation near 125.3 | Predictive | DEF-8293 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-01-17 | 2026-09-01 | FALSE | 120 | 4 technicians, cable jointing kit | TRUE | FULL | 2026-09-04 | 22:00 | 00:00 | PENDING
SMMS-034 | SIGNAL & TELECOM | SMMS | STN04 | SEC05 | SIG-175 | SIGNAL | Repair point machine malfunction near 38.5 | Corrective | DEF-5930 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2025-10-13 | 2026-09-02 | FALSE | 240 | 2 technicians, relay test set | TRUE | PARTIAL | 2026-09-04 | 02:00 | 06:00 | PENDING
SMMS-035 | SIGNAL & TELECOM | SMMS | STN01 | SEC02 | SIG-176 | SIGNAL | Replace faulty signal relay near 90.6 | Preventive | DEF-9802 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2025-11-13 | 2026-09-17 | FALSE | 180 | 3 signal technicians, testing kit | TRUE | PARTIAL | 2026-09-17 | 20:00 | 22:00 | PENDING
SMMS-036 | SIGNAL & TELECOM | SMMS | STN15 | SEC04 | SIG-196 | SIGNAL | Replace degraded signal cable insulation near 50.5 | Preventive | DEF-1043 | LOW | LOW | FALSE | NORMAL | 2 | 2025-09-19 | 2026-08-16 | TRUE | 180 | 2 technicians, relay test set | TRUE | PARTIAL | 2026-08-26 | 01:00 | 03:00 | PENDING
SMMS-037 | SIGNAL & TELECOM | SMMS | STN06 | SEC06 | SIG-176 | SIGNAL | Update interlocking software at 64.3 | Preventive | DEF-3706 | LOW | LOW | FALSE | NORMAL | 1 | 2026-06-10 | 2026-09-17 | FALSE | 300 | 2 signal engineers, laptop with S&T software | TRUE | PARTIAL | 2026-09-19 | 20:00 | 00:00 | PENDING
SMMS-038 | SIGNAL & TELECOM | SMMS | STN16 | SEC05 | SIG-133 | SIGNAL | Repair point machine malfunction near 150.5 | Corrective | DEF-1860 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2026-02-14 | 2026-09-15 | FALSE | 150 | 4 technicians, cable jointing kit | TRUE | PARTIAL | 2026-09-19 | 01:00 | 05:00 | PENDING
SMMS-039 | SIGNAL & TELECOM | SMMS | STN06 | SEC08 | SIG-172 | SIGNAL | Repair axle counter fault near 154.1 | Preventive | DEF-4898 | CRITICAL | HIGH | TRUE | OUT_OF_SERVICE | 1 | 2025-11-12 | 2026-08-31 | FALSE | 120 | 2 signal engineers, laptop with S&T software | TRUE | FULL | 2026-08-31 | 00:00 | 02:00 | PENDING
SMMS-040 | SIGNAL & TELECOM | SMMS | STN08 | SEC05 | SIG-120 | SIGNAL | Update interlocking software at 146.6 | Corrective | DEF-8447 | HIGH | HIGH | TRUE | RESTRICTED | 2 | 2026-05-12 | 2026-09-16 | FALSE | 150 | 4 technicians, cable jointing kit | TRUE | FULL | 2026-09-17 | 04:00 | 07:00 | APPROVED