## Sheet1
Request_id | Department | Source_system | Location | Section_id | Asset_id | Asset_type | Work_description | Maintenance_category | Defect_id | Defect_severity | Failure_risk | Safety_related | Asset_operational_status | Affected_asset_quantity | Last_maintenance_date | Due_date | Overdue | Estimated_duration_minutes | Required_resources | Requires_block | Block_type_required | Preferred_date | Preferred_start_time | Preferred_end_time | Request_status
TDMS-001 | TRACTION DISTRIBUTION | TDMS | STN02 | SEC01 | OHE-100 | OHE | Improve earthing resistance near 28.8 | Corrective | DEF-9611 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-04-19 | 2026-08-24 | TRUE | 150 | 6 technicians, transformer test kit | TRUE | PARTIAL | 2026-08-30 | 04:00 | 08:00 | APPROVED
TDMS-002 | TRACTION DISTRIBUTION | TDMS | STN08 | SEC02 | OHE-153 | OHE | Improve earthing resistance near 184.8 | Corrective | DEF-4723 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-03-01 | 2026-09-02 | FALSE | 180 | 5 linemen, feeder testing equipment | TRUE | PARTIAL | 2026-09-04 | 00:00 | 04:00 | COMPLETED
TDMS-003 | TRACTION DISTRIBUTION | TDMS | STN06 | SEC04 | OHE-159 | OHE | Traction transformer scheduled maintenance at 12.3 | Predictive | DEF-4495 | LOW | LOW | FALSE | NORMAL | 2 | 2025-08-31 | 2026-08-18 | TRUE | 240 | 4 linemen, insulated tools, OHE testing van | TRUE | PARTIAL | 2026-08-30 | 02:00 | 06:00 | PENDING
TDMS-004 | TRACTION DISTRIBUTION | TDMS | STN15 | SEC03 | OHE-197 | OHE | Replace insulator with flashover risk near 151.8 | Corrective | DEF-8325 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2025-10-24 | 2026-08-28 | FALSE | 150 | 3 linemen, tension measuring kit | TRUE | FULL | 2026-08-31 | 01:00 | 05:00 | APPROVED
TDMS-005 | TRACTION DISTRIBUTION | TDMS | STN09 | SEC01 | OHE-165 | OHE | Repair feeder cable fault near 132.9 | Corrective | DEF-4564 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-02-06 | 2026-08-16 | TRUE | 150 | 5 linemen, feeder testing equipment | TRUE | PARTIAL | 2026-08-29 | 01:00 | 05:00 | PENDING
TDMS-006 | TRACTION DISTRIBUTION | TDMS | STN03 | SEC06 | OHE-148 | OHE | Replace insulator with flashover risk near 30.4 | Corrective | DEF-9508 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-04-26 | 2026-08-16 | TRUE | 180 | 6 technicians, transformer test kit | TRUE | PARTIAL | 2026-08-27 | 04:00 | 07:00 | APPROVED
TDMS-007 | TRACTION DISTRIBUTION | TDMS | STN14 | SEC04 | OHE-161 | OHE | Improve earthing resistance near 32.9 | Corrective | DEF-3228 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-04-22 | 2026-08-17 | TRUE | 180 | 6 technicians, transformer test kit | TRUE | PARTIAL | 2026-08-26 | 02:00 | 05:00 | APPROVED
TDMS-008 | TRACTION DISTRIBUTION | TDMS | STN12 | SEC04 | OHE-128 | OHE | Improve earthing resistance near 159.4 | Corrective | DEF-7069 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2025-11-08 | 2026-09-09 | FALSE | 120 | 4 linemen, insulated tools, OHE testing van | TRUE | FULL | 2026-09-10 | 04:00 | 08:00 | COMPLETED
TDMS-009 | TRACTION DISTRIBUTION | TDMS | STN12 | SEC08 | OHE-185 | OHE | Repair feeder cable fault near 109.7 | Corrective | DEF-7130 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2025-07-23 | 2026-08-19 | TRUE | 240 | 5 linemen, feeder testing equipment | TRUE | PARTIAL | 2026-08-26 | 20:00 | 00:00 | PENDING
TDMS-010 | TRACTION DISTRIBUTION | TDMS | STN09 | SEC07 | OHE-128 | OHE | Traction transformer scheduled maintenance at 96.2 | Corrective | DEF-7593 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2025-12-12 | 2026-09-05 | FALSE | 180 | 3 linemen, tension measuring kit | TRUE | PARTIAL | 2026-09-07 | 04:00 | 08:00 | PENDING
TDMS-011 | TRACTION DISTRIBUTION | TDMS | STN10 | SEC02 | OHE-189 | OHE | Traction transformer scheduled maintenance at 142.4 | Predictive | DEF-7412 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-04-10 | 2026-09-14 | FALSE | 180 | 4 linemen, insulated tools, OHE testing van | TRUE | PARTIAL | 2026-09-18 | 02:00 | 06:00 | COMPLETED
TDMS-012 | TRACTION DISTRIBUTION | TDMS | STN03 | SEC07 | OHE-103 | OHE | Improve earthing resistance near 96.7 | Corrective | DEF-6300 | HIGH | HIGH | FALSE | RESTRICTED | 1 | 2026-01-24 | 2026-09-14 | FALSE | 150 | 3 linemen, tension measuring kit | TRUE | FULL | 2026-09-19 | 02:00 | 05:00 | APPROVED
TDMS-013 | TRACTION DISTRIBUTION | TDMS | STN14 | SEC06 | OHE-178 | OHE | Repair feeder cable fault near 181.6 | Corrective | DEF-5524 | HIGH | HIGH | TRUE | RESTRICTED | 2 | 2026-06-11 | 2026-08-28 | FALSE | 150 | 6 technicians, transformer test kit | TRUE | FULL | 2026-08-28 | 22:00 | 00:00 | COMPLETED
TDMS-014 | TRACTION DISTRIBUTION | TDMS | STN05 | SEC03 | OHE-177 | OHE | Repair feeder cable fault near 131.4 | Corrective | DEF-4743 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-01-19 | 2026-09-15 | FALSE | 120 | 4 linemen, insulated tools, OHE testing van | TRUE | FULL | 2026-09-17 | 04:00 | 06:00 | COMPLETED
TDMS-015 | TRACTION DISTRIBUTION | TDMS | STN11 | SEC01 | OHE-133 | OHE | Traction transformer scheduled maintenance at 49.3 | Corrective | DEF-1317 | LOW | LOW | FALSE | NORMAL | 1 | 2025-07-29 | 2026-09-19 | FALSE | 300 | 3 linemen, tension measuring kit | TRUE | PARTIAL | 2026-09-19 | 20:00 | 00:00 | APPROVED
TDMS-016 | TRACTION DISTRIBUTION | TDMS | STN14 | SEC04 | OHE-136 | OHE | Replace insulator with flashover risk near 157.5 | Corrective | DEF-9748 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2026-01-07 | 2026-09-15 | FALSE | 150 | 3 linemen, tension measuring kit | TRUE | PARTIAL | 2026-09-19 | 02:00 | 05:00 | PENDING
TDMS-017 | TRACTION DISTRIBUTION | TDMS | STN16 | SEC03 | OHE-105 | OHE | Re-tension OHE wire near 167.3 | Corrective | DEF-7761 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2026-05-05 | 2026-09-03 | FALSE | 150 | 5 linemen, feeder testing equipment | TRUE | PARTIAL | 2026-09-03 | 04:00 | 08:00 | PENDING
TDMS-018 | TRACTION DISTRIBUTION | TDMS | STN05 | SEC07 | OHE-172 | OHE | Repair feeder cable fault near 51.8 | Predictive | DEF-3057 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2025-12-20 | 2026-09-04 | FALSE | 150 | 3 linemen, tension measuring kit | TRUE | PARTIAL | 2026-09-05 | 02:00 | 04:00 | PENDING
TDMS-019 | TRACTION DISTRIBUTION | TDMS | STN09 | SEC05 | OHE-188 | OHE | Replace insulator with flashover risk near 47.7 | Corrective | DEF-5128 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2026-06-19 | 2026-09-14 | FALSE | 180 | 3 linemen, tension measuring kit | TRUE | PARTIAL | 2026-09-18 | 22:00 | 00:00 | PENDING
TDMS-020 | TRACTION DISTRIBUTION | TDMS | STN13 | SEC02 | OHE-142 | OHE | Replace insulator with flashover risk near 166.1 | Predictive | DEF-9889 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2026-01-31 | 2026-09-06 | FALSE | 150 | 5 linemen, feeder testing equipment | TRUE | PARTIAL | 2026-09-11 | 20:00 | 22:00 | PENDING
TDMS-021 | TRACTION DISTRIBUTION | TDMS | STN07 | SEC05 | OHE-169 | OHE | Improve earthing resistance near 46.4 | Corrective | DEF-3406 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2025-11-30 | 2026-08-24 | TRUE | 150 | 4 linemen, insulated tools, OHE testing van | TRUE | PARTIAL | 2026-08-29 | 04:00 | 08:00 | APPROVED
TDMS-022 | TRACTION DISTRIBUTION | TDMS | STN05 | SEC08 | OHE-135 | OHE | Replace insulator with flashover risk near 85.0 | Preventive | DEF-5489 | LOW | LOW | FALSE | NORMAL | 1 | 2026-01-12 | 2026-08-16 | TRUE | 180 | 4 linemen, insulated tools, OHE testing van | TRUE | PARTIAL | 2026-08-27 | 20:00 | 00:00 | PENDING
TDMS-023 | TRACTION DISTRIBUTION | TDMS | STN01 | SEC05 | OHE-123 | OHE | Replace insulator with flashover risk near 108.4 | Corrective | DEF-3289 | HIGH | HIGH | FALSE | RESTRICTED | 1 | 2026-05-25 | 2026-08-15 | TRUE | 150 | 6 technicians, transformer test kit | TRUE | FULL | 2026-08-27 | 22:00 | 00:00 | PENDING
TDMS-024 | TRACTION DISTRIBUTION | TDMS | STN08 | SEC07 | OHE-156 | OHE | Replace insulator with flashover risk near 108.1 | Preventive | DEF-1769 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2025-09-18 | 2026-08-31 | FALSE | 120 | 4 linemen, insulated tools, OHE testing van | TRUE | FULL | 2026-09-02 | 01:00 | 04:00 | APPROVED
TDMS-025 | TRACTION DISTRIBUTION | TDMS | STN03 | SEC01 | OHE-146 | OHE | Repair feeder cable fault near 144.4 | Corrective | DEF-9638 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-05-25 | 2026-09-16 | FALSE | 180 | 6 technicians, transformer test kit | TRUE | FULL | 2026-09-19 | 00:00 | 02:00 | PENDING
TDMS-026 | TRACTION DISTRIBUTION | TDMS | STN01 | SEC02 | OHE-173 | OHE | Traction transformer scheduled maintenance at 178.2 | Corrective | DEF-6302 | LOW | LOW | FALSE | NORMAL | 2 | 2025-12-03 | 2026-09-10 | FALSE | 300 | 5 linemen, feeder testing equipment | TRUE | PARTIAL | 2026-09-12 | 20:00 | 22:00 | APPROVED
TDMS-027 | TRACTION DISTRIBUTION | TDMS | STN11 | SEC06 | OHE-176 | OHE | Traction transformer scheduled maintenance at 121.0 | Corrective | DEF-6485 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2025-12-27 | 2026-09-03 | FALSE | 120 | 4 linemen, insulated tools, OHE testing van | TRUE | FULL | 2026-09-05 | 00:00 | 04:00 | APPROVED
TDMS-028 | TRACTION DISTRIBUTION | TDMS | STN14 | SEC04 | OHE-102 | OHE | Re-tension OHE wire near 37.8 | Corrective | DEF-9234 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-04-08 | 2026-08-24 | TRUE | 180 | 4 linemen, insulated tools, OHE testing van | TRUE | PARTIAL | 2026-08-27 | 02:00 | 04:00 | PENDING
TDMS-029 | TRACTION DISTRIBUTION | TDMS | STN11 | SEC04 | OHE-155 | OHE | Replace insulator with flashover risk near 8.8 | Corrective | DEF-4598 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2026-01-13 | 2026-08-19 | TRUE | 180 | 3 linemen, tension measuring kit | TRUE | PARTIAL | 2026-08-29 | 00:00 | 04:00 | COMPLETED
TDMS-030 | TRACTION DISTRIBUTION | TDMS | STN13 | SEC07 | OHE-182 | OHE | Repair feeder cable fault near 180.3 | Corrective | DEF-6645 | CRITICAL | HIGH | FALSE | OUT_OF_SERVICE | 2 | 2026-03-25 | 2026-09-06 | FALSE | 150 | 4 linemen, insulated tools, OHE testing van | TRUE | FULL | 2026-09-10 | 00:00 | 02:00 | PENDING
TDMS-031 | TRACTION DISTRIBUTION | TDMS | STN02 | SEC08 | OHE-165 | OHE | Traction transformer scheduled maintenance at 85.7 | Predictive | DEF-9654 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 2 | 2025-11-24 | 2026-09-08 | FALSE | 180 | 5 linemen, feeder testing equipment | TRUE | PARTIAL | 2026-09-12 | 01:00 | 04:00 | APPROVED
TDMS-032 | TRACTION DISTRIBUTION | TDMS | STN07 | SEC06 | OHE-194 | OHE | Traction transformer scheduled maintenance at 33.1 | Corrective | DEF-7587 | MEDIUM | MEDIUM | FALSE | RESTRICTED | 1 | 2026-01-09 | 2026-08-31 | FALSE | 150 | 6 technicians, transformer test kit | TRUE | PARTIAL | 2026-09-05 | 20:00 | 23:00 | PENDING
TDMS-033 | TRACTION DISTRIBUTION | TDMS | STN02 | SEC03 | OHE-191 | OHE | Re-tension OHE wire near 158.4 | Corrective | DEF-9481 | HIGH | HIGH | FALSE | RESTRICTED | 2 | 2025-10-08 | 2026-08-31 | FALSE | 120 | 4 linemen, insulated tools, OHE testing van | TRUE | FULL | 2026-09-02 | 00:00 | 02:00 | COMPLETED
TDMS-034 | TRACTION DISTRIBUTION | TDMS | STN08 | SEC05 | OHE-109 | OHE | Replace insulator with flashover risk near 182.9 | Preventive | DEF-1916 | HIGH | HIGH | FALSE | RESTRICTED | 1 | 2026-05-20 | 2026-08-21 | TRUE | 120 | 5 linemen, feeder testing equipment | TRUE | FULL | 2026-08-29 | 04:00 | 07:00 | PENDING
TDMS-035 | TRACTION DISTRIBUTION | TDMS | STN13 | SEC06 | OHE-103 | OHE | Replace insulator with flashover risk near 181.7 | Preventive | DEF-8629 | HIGH | HIGH | FALSE | RESTRICTED | 1 | 2026-01-30 | 2026-08-22 | TRUE | 120 | 3 linemen, tension measuring kit | TRUE | FULL | 2026-08-28 | 01:00 | 05:00 | APPROVED
TDMS-036 | TRACTION DISTRIBUTION | TDMS | STN09 | SEC04 | OHE-184 | OHE | Traction transformer scheduled maintenance at 108.6 | Preventive | DEF-4433 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2025-12-15 | 2026-08-15 | TRUE | 120 | 6 technicians, transformer test kit | TRUE | FULL | 2026-08-27 | 22:00 | 01:00 | PENDING
TDMS-037 | TRACTION DISTRIBUTION | TDMS | STN03 | SEC05 | OHE-188 | OHE | Improve earthing resistance near 179.1 | Corrective | DEF-6903 | HIGH | HIGH | FALSE | RESTRICTED | 2 | 2025-08-12 | 2026-09-06 | FALSE | 120 | 3 linemen, tension measuring kit | TRUE | FULL | 2026-09-08 | 01:00 | 03:00 | PENDING
TDMS-038 | TRACTION DISTRIBUTION | TDMS | STN04 | SEC06 | OHE-144 | OHE | Traction transformer scheduled maintenance at 156.7 | Corrective | DEF-7846 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-02-04 | 2026-09-13 | FALSE | 150 | 4 linemen, insulated tools, OHE testing van | TRUE | FULL | 2026-09-14 | 20:00 | 22:00 | COMPLETED
TDMS-039 | TRACTION DISTRIBUTION | TDMS | STN14 | SEC02 | OHE-176 | OHE | Traction transformer scheduled maintenance at 130.2 | Corrective | DEF-2051 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-03-03 | 2026-09-14 | FALSE | 150 | 6 technicians, transformer test kit | TRUE | FULL | 2026-09-17 | 01:00 | 05:00 | APPROVED
TDMS-040 | TRACTION DISTRIBUTION | TDMS | STN09 | SEC01 | OHE-149 | OHE | Replace insulator with flashover risk near 129.3 | Corrective | DEF-6596 | HIGH | HIGH | TRUE | RESTRICTED | 1 | 2026-06-19 | 2026-09-10 | FALSE | 180 | 4 linemen, insulated tools, OHE testing van | TRUE | FULL | 2026-09-12 | 01:00 | 05:00 | PENDING